## MNT Pivot Overview
Row Labels | Count of DR Number
In Progress | 7
Lawley | 3
Mohadin | 2
Mamelodi | 2
Open | 1
Mohadin | 1
Pending Company | 5
Mohadin | 5
Resolved | 324
Lawley | 196
Mohadin | 121
Mamelodi | 7
Grand Total | 337

## MNT Tickets Logged
Date Captured by Velocity | Area | Status | FT Ref | DR Number | Issue | Responsible Technician | Date Submitted to Velocity Tech | Date Resolved | Posted to FT MNT Group | Comments | Updated on Qcontact
2025-10-21 | Mohadin | Resolved | FT406824 | DR1854675 | Connectivity | Velocity MNT Tech | 2025-10-22 | 2025-10-23 | Yes | PON Down, Restored | Yes
2025-10-21 | Mohadin | Resolved | FT319119 | DR1853335 | Connectivity | Velocity MNT Tech | 2025-10-22 | 2025-10-23 | Yes | PON Down, Restored | Yes
2025-10-21 | Lawley | Resolved | FT320673 | DR1750547 | Connectivity | Velocity MNT Tech | 2025-10-22 | 2025-10-22 | Yes | No Issue found | Yes
2025-10-21 | Lawley | Resolved | FT320677 | DR1750235 | Connectivity | Velocity MNT Tech | 2025-10-22 | 2025-10-22 | Yes | No Issue found | Yes
2025-10-21 | Lawley | Resolved | FT328991 | DR1751327 | Connectivity | Velocity MNT Tech | 2025-10-22 | 2025-10-22 | Yes | Poor Splice in the SJC | Yes
2025-10-21 | Mohadin | Resolved | FT341306 | DR1854813 | Connectivity | Velocity MNT Tech | 2025-10-22 | 2025-10-23 | Yes | Splice Broken in SJC | Yes
2025-10-21 | Lawley | Resolved | FT343499 | DR17513117 | Connectivity | Velocity MNT Tech | 2025-10-22 | 2025-10-22 | Yes |  | Yes
2025-10-21 | Mohadin | Resolved | FT346156 | DR1854298 | Connectivity | Velocity MNT Tech | 2025-10-22 | 2025-10-23 | Yes | Bad Splice in SJC, respliced | Yes
2025-10-21 | Lawley | Resolved | FT355409 | DR1750991 | Connectivity | Velocity MNT Tech | 2025-10-22 | 2025-10-22 | Yes |  | Yes
2025-10-21 | Mohadin | Resolved | FT376553 | DR1853340 | Connectivity | Velocity MNT Tech | 2025-10-22 | 2025-10-23 | Yes | Bad Splice in SJC, respliced | Yes
2025-10-21 | Mohadin | Resolved | FT377455 | DR1854697 | Connectivity | Velocity MNT Tech | 2025-11-11 | 2025-11-12 | Yes | Loose Connection at router | Yes
2025-10-21 | Mohadin | Resolved | FT377772 | DR1853549 | Connectivity | Velocity MNT Tech | 2025-10-27 | 2025-11-10 |  |  | Yes
2025-10-21 | Mohadin | Resolved | FT377909 | DR1854701 | Connectivity | Velocity MNT Tech | 2025-11-11 | 2025-11-12 | Yes | Loose Connection at SJC | Yes
2025-10-21 | Mohadin | Resolved | FT384052 | DR1853607 | Connectivity | Velocity MNT Tech | 2025-10-27 | 2025-11-10 | Yes | DR# was incorrect is actually DR1853612 | Yes
2025-10-21 | Lawley | Resolved | FT393601 | DR1749894 | Connectivity | Velocity MNT Tech | 2025-10-22 | 2025-10-23 | Yes | Splitter in Feeder Joint Problematic | Yes
2025-10-21 | Lawley | Resolved | FT394531 | DR1750989 | Connectivity | Velocity MNT Tech | 2025-10-22 | 2025-10-23 | Yes | Splitter in Feeder Joint Problematic | Yes
2025-10-21 | Lawley | Resolved | FT394817 | DR1750887 | Connectivity | Velocity MNT Tech | 2025-10-22 | 2025-10-23 | Yes | Splitter in Feeder Joint Problematic | Yes
2025-10-21 | Lawley | Resolved | FT394960 | DR1750879 | Connectivity | Velocity MNT Tech | 2025-10-23 | 2025-11-17 |  | Customer Confirmed all in order 2025/11/17 | Yes
2025-10-21 | Mohadin | Resolved | FT395837 | DR1854718 | Connectivity | Velocity MNT Tech | 2025-10-27 | 2025-11-10 | Yes | No Fault Found | Yes
2025-10-21 | Mohadin | Resolved | FT396526 | DR1854703 | Connectivity | Velocity MNT Tech | 2025-11-11 | 2025-11-12 | Yes | Rebooted Device | Yes
2025-10-21 | Lawley | Resolved | FT397178 | DR1750776 | Connectivity | Velocity MNT Tech | 2025-10-23 | 2025-11-19 |  | Ticket Closed, client never available | Yes
2025-10-21 | Lawley | Resolved | FT397364 | DR1752757 | Connectivity | Velocity MNT Tech | 2025-10-23 | 2025-10-23 | Yes | No Issue found | Yes
2025-10-21 | Lawley | Resolved | FT397797 | DR1750983 | Connectivity | Velocity MNT Tech | 2025-10-23 | 2025-10-23 | Yes | Splitter in Feeder Joint Problematic | Yes
2025-10-21 | Mohadin | Resolved | FT398165 | DR1854675 | Connectivity | Velocity MNT Tech | 2025-10-22 | 2025-10-23 | Yes | PON Down, Restored | Yes
2025-10-21 | Lawley | Resolved | FT398521 | DR1748888 | Connectivity | Velocity MNT Tech | 2025-10-23 | 2025-10-23 | Yes | No Issue found | Yes
2025-10-21 | Mohadin | Resolved | FT398591 | DR1854719 | Connectivity | Velocity MNT Tech | 2025-11-11 | 2025-11-12 | Yes | No Fault Found | Yes
2025-10-21 | Lawley | Resolved | FT398611 | DR1749872 | Connectivity | Velocity MNT Tech | 2025-10-23 | 2025-10-23 | Yes | Splitter in Feeder Joint Problematic | Yes
2025-10-21 | Lawley | Resolved | FT399069 | DR1750900 | Connectivity | Velocity MNT Tech | 2025-10-23 | 2025-10-23 | Yes | Splitter in Feeder Joint Problematic | Yes
2025-10-21 | Lawley | Resolved | FT399925 | DR1748833 | Connectivity | Velocity MNT Tech | 2025-10-23 | 2025-10-23 | Yes | No Issue found | Yes
2025-10-21 | Mohadin | Resolved | FT400789 | DR1853539 | Connectivity | Velocity MNT Tech | 2025-11-11 | 2025-11-12 | Yes | No Fault Found | Yes
2025-10-21 | Lawley | Resolved | FT404137 | DR1750993 | Connectivity | Velocity MNT Tech | 2025-10-23 | 2025-10-23 | Yes |  | Yes
2025-10-21 | Lawley | Resolved | FT404663 | DR1750753 | Connectivity | Velocity MNT Tech | 2025-10-23 | 2025-10-23 | Yes | Splitter in Feeder Joint Problematic | Yes
2025-10-21 | Lawley | Resolved | FT409143 | DR1758717 | Connectivity | Velocity MNT Tech | 2025-10-23 | 2025-10-24 | Yes | Kink in HD rectified | Yes
2025-10-21 | Lawley | Resolved | FT317766 | DR1753037 | Connection Issue | Velocity MNT Tech | 2025-10-23 | 2025-11-04 | Yes | No Fault Found | Yes
2025-10-21 | Lawley | Resolved | FT320718 | DR1751354 | Connection Issue | Velocity MNT Tech | 2025-10-24 | 2025-10-24 | Yes | Loose Connection in SJC | Yes
2025-10-21 | Lawley | Resolved | FT343783 | DR1748467 | Connection Issue | Velocity MNT Tech | 2025-10-27 | 2025-10-27 | Yes | Broken Fibre in SJC | Yes
2025-10-21 | Lawley | Resolved | FT343850 | DR1750331 | Connection Issue | Velocity MNT Tech | 2025-10-27 | 2025-11-03 | Yes | Loose Pigtail reconnected | Yes
2025-10-21 | Lawley | Resolved | FT344833 | DR1748638 | Connection Issue | Velocity MNT Tech | 2025-10-27 | 2025-10-27 | Yes | No Issue found | Yes
2025-10-21 | Lawley | Resolved | FT354859 | DR1752718 | Connection Issue | Velocity MNT Tech | 2025-10-27 | 2025-10-27 | Yes | No Issue Found | Yes
2025-10-21 | Lawley | Resolved | FT359911 | DR1750859 | Connection Issue | Velocity MNT Tech | 2025-10-24 | 2025-10-24 | Yes | Dirty Mid Coupler | Yes
2025-10-21 | Mohadin | Resolved | FT369973 | DR1853939 | Connection Issue | Velocity MNT Tech | 2025-11-11 | 2025-11-12 | Yes | No Fault Found | Yes
2025-10-21 | Lawley | Resolved | FT372265 | DR1733148 | Connection Issue | Velocity MNT Tech | 2025-10-27 | 2025-10-27 | Yes | No ptached in SJC | Yes
2025-10-21 | Mohadin | Resolved | FT373454 | DR1854578 | Connection Issue | Velocity MNT Tech | 2025-11-11 | 2025-11-12 |  |  | Yes
2025-10-21 | Lawley | Resolved | FT375835 | DR1750991 | Connection Issue | Velocity MNT Tech | 2025-10-22 | 2025-10-22 | Yes |  | Yes
2025-10-21 | Lawley | Resolved | FT376339 | DR1748459 | Connection Issue | Velocity MNT Tech | 2025-10-27 | 2025-10-27 | Yes | No Issue found | Yes
2025-10-21 | Mohadin | Resolved | FT378595 | DR1854263 | Connection Issue | Velocity MNT Tech | 2025-11-11 | 2025-11-12 | Yes | Rebooted Device | Yes
2025-10-21 | Mohadin | Resolved | FT383390 | DR1853549 | Connection Issue | Velocity MNT Tech | 2025-11-10 | 2025-11-10 |  |  | Yes
2025-10-21 | Mohadin | Resolved | FT384363 | DR1853607 | Connection Issue | Velocity MNT Tech | 2025-11-10 | 2025-11-10 | Yes | DR# was incorrect is actually DR1853612 | Yes
2025-10-21 | Mohadin | Resolved | FT389161 | DR1854578 | Connection Issue | Velocity MNT Tech | 2025-11-11 | 2025-11-12 |  |  | Yes
2025-10-21 | Lawley | Resolved | FT390724 | DR1750813 | Connection Issue | Velocity MNT Tech | 2025-10-24 | 2025-10-29 | Yes | Seems to be a product issue | Yes
2025-10-21 | Lawley | Resolved | FT391500 | DR1750800 | Connection Issue | Velocity MNT Tech | 2025-10-24 | 2025-11-03 | Yes | Rebooted Device | Yes
2025-10-21 | Lawley | Resolved | FT391536 | DR1750862 | Connection Issue | Velocity MNT Tech | 2025-10-24 | 2025-10-24 | Yes | No Issue Found | Yes
2025-10-21 | Lawley | Resolved | FT392865 | DR1751354 | Connection Issue | Velocity MNT Tech | 2025-10-24 | 2025-10-24 | Yes | Loose Connection in SJC | Yes
2025-10-21 | Lawley | Resolved | FT393328 | DR1750865 | Connection Issue | Velocity MNT Tech | 2025-10-27 | 2025-11-03 | Yes | Pigtail Damaged | Yes
2025-10-21 | Lawley | Resolved | FT393438 | DR1748345 | Connection Issue | Velocity MNT Tech | 2025-10-24 | 2025-10-24 | Yes | No Issue found | Yes
2025-10-21 | Lawley | Resolved | FT393451 | DR1751099 | Connection Issue | Velocity MNT Tech | 2025-10-24 | 2025-10-24 | Yes | No Issue Found | Yes
2025-10-21 | Lawley | Resolved | FT393644 | DR1751099 | Connection Issue | Velocity MNT Tech | 2025-10-24 | 2025-10-24 | Yes | No Issue Found | Yes
2025-10-21 | Lawley | Resolved | FT394843 | DR1751662 | Connection Issue | Velocity MNT Tech | 2025-10-27 | 2025-10-24 | Yes | No Issue found | Yes
2025-10-21 | Lawley | Resolved | FT395087 | DR1750800 | Connection Issue | Velocity MNT Tech | 2025-10-27 | 2025-11-03 | Yes | Rebooted Device | Yes
2025-10-21 | Lawley | Resolved | FT395293 | DR1750862 | Connection Issue | Velocity MNT Tech | 2025-10-24 | 2025-10-24 | Yes | No Issue Found | Yes
2025-10-21 | Lawley | Resolved | FT396144 | DR1751099 | Connection Issue | Velocity MNT Tech | 2025-10-24 | 2025-10-24 | Yes | No Issue Found | Yes
2025-10-21 | Lawley | Resolved | FT396245 | DR1750851 | Connection Issue | Velocity MNT Tech | 2025-10-31 | 2025-11-03 | Yes | No Fault Found | Yes
2025-10-21 | Lawley | Resolved | FT396295 | DR1752495 | Connection Issue | Velocity MNT Tech | 2025-10-31 | 2025-10-31 | Yes | No Fault Found | Yes
2025-10-21 | Lawley | Resolved | FT396738 | DR1748583 | Connection Issue | Velocity MNT Tech | 2025-10-31 | 2025-11-03 | Yes | Device Lost Connection - Rebooted | Yes
2025-10-21 | Lawley | Resolved | FT396872 | DR1752764 | Connection Issue | Velocity MNT Tech | 2025-10-30 | 2025-10-30 |  | No Issue | Yes
2025-10-21 | Lawley | Resolved | FT397295 | DR1752662 | Connection Issue | Velocity MNT Tech | 2025-10-30 | 2025-10-30 |  | No Issue | Yes
2025-10-21 | Mohadin | Resolved | FT397346 | DR1854455 | Connection Issue | Velocity MNT Tech | 2025-11-10 | 2025-11-10 | Yes | Rebooted Device | Yes
2025-10-21 | Lawley | Resolved | FT397349 | DR1748345 | Connection Issue | Velocity MNT Tech | 2025-10-24 | 2025-10-24 | Yes | No Issue found | Yes
2025-10-21 | Lawley | Resolved | FT397391 | DR1748669 | Connection Issue | Velocity MNT Tech | 2025-10-31 | 2025-10-31 | Yes | No Issue | Yes
2025-10-21 | Lawley | Resolved | FT397435 | DR1749906 | Connection Issue | Velocity MNT Tech | 2025-10-24 | 2025-10-24 | Yes | Waiting on Photos | Yes
2025-10-21 | Lawley | Resolved | FT397640 | DR1748832 | Connection Issue | Velocity MNT Tech | 2025-10-31 | 2025-11-03 | Yes | No Access / Unavailable | Yes
2025-10-21 | Lawley | Resolved | FT397814 | DR1749894 | Connection Issue | Velocity MNT Tech | 2025-10-22 | 2025-10-23 | Yes | Splitter in Feeder Joint Problematic | Yes
2025-10-21 | Lawley | Resolved | FT398515 | DR1748523 | Connection Issue | Velocity MNT Tech | 2025-10-31 | 2025-11-03 | Yes | No Fault Found | Yes
2025-10-21 | Lawley | Resolved | FT398528 | DR1748539 | Connection Issue | Velocity MNT Tech | 2025-10-29 | 2025-10-29 | Yes | Broken Fibre in SJC | Yes
2025-10-21 | Lawley | Resolved | FT398576 | DR1749898 | Connection Issue | Velocity MNT Tech | 2025-10-31 | 2025-10-31 | Yes | No Issue | Yes
2025-10-21 | Lawley | Resolved | FT398657 | DR1748882 | Connection Issue | Velocity MNT Tech | 2025-10-30 | 2025-10-30 |  | No Issue | Yes
2025-10-21 | Lawley | Resolved | FT398723 | DR1748487 | Connection Issue | Velocity MNT Tech | 2025-10-31 | 2025-10-31 | Yes | No Issue | Yes
2025-10-21 | Lawley | Resolved | FT399410 | DR1749906 | Connection Issue | Velocity MNT Tech | 2025-10-24 | 2025-10-24 | Yes | Waiting on Photos | Yes
2025-10-21 | Lawley | Resolved | FT400566 | No DR | Connectivity | Velocity MNT Tech | 2025-10-31 | 2025-11-03 | Yes | Requires Activation and DR# | Yes
2025-10-21 | Lawley | Resolved | FT403874 | DR1750125 | Connection Issue | Velocity MNT Tech | 2025-10-31 | 2025-10-31 | Yes | Broken Fibre in Joint | Yes
2025-10-21 | Lawley | Resolved | FT404691 | DR1751010 | Connection Issue | Velocity MNT Tech | 2025-10-31 | 2025-10-31 | Yes | Respliced leg on 1:8 Way Splitter | Yes
2025-10-21 | Lawley | Resolved | FT404827 | DR1750813 | Connection Issue | Velocity MNT Tech | 2025-10-29 | 2025-10-29 | Yes | Seems to be a product issue | Yes
2025-10-21 | Mohadin | Resolved | FT405109 | DR1854718 | Connection Issue | Velocity MNT Tech | 2025-11-10 | 2025-11-10 | Yes | No Fault Found | Yes
2025-10-21 | Lawley | Resolved | FT405790 | DR1750983 | Connection Issue | Velocity MNT Tech | 2025-10-22 | 2025-10-23 | Yes | Splitter in Feeder Joint Problematic | Yes
2025-10-21 | Lawley | Resolved | FT407895 | DR1752457 | Connection Issue | Velocity MNT Tech | 2025-10-30 | 2025-10-30 |  | No Issue | Yes
2025-10-21 | Lawley | Resolved | FT288976 | DR1751164 | Connectivity | Velocity MNT Tech | 2025-10-30 | 2025-10-30 |  | No Issue | Yes
2025-10-21 | Lawley | Resolved | FT290842 | DR1752592 | Connectivity | Velocity MNT Tech | 2025-10-30 | 2025-10-30 |  | Device Cannot Authenticate Support to Assist | Yes
2025-10-21 | Lawley | Resolved | FT293154 | DR1749982 | Connectivity | Velocity MNT Tech | 2025-10-30 | 2025-10-30 |  | Device needs to be activated | Yes
2025-10-21 | Lawley | Resolved | FT294484 | DR1750325 | Connectivity | Velocity MNT Tech | 2025-10-30 | 2025-11-03 | Yes | Cleaned Mid Coupler | Yes
2025-10-21 | Lawley | Resolved | FT312102 | DR1753035 | Connectivity | Velocity MNT Tech | 2025-10-30 | 2025-11-04 | Yes | No Fault Found | Yes
2025-10-21 | Lawley | Resolved | FT353253 | DR1750993 | Connectivity | Velocity MNT Tech | 2025-10-22 | 2025-10-23 | Yes | Duplicate | Yes
2025-10-21 | Lawley | Resolved | FT353829 | DR1750991 | Connectivity | Velocity MNT Tech | 2025-10-24 | 2025-10-24 | Yes | Duplicate | Yes
2025-10-21 | Lawley | Resolved | FT353871 | DR1750991 | Connectivity | Velocity MNT Tech | 2025-10-24 | 2025-10-24 | Yes | Splitter in Feeder Joint Problematic | Yes
2025-10-21 | Lawley | Resolved | FT368795 | DR1750859 | Connectivity | Velocity MNT Tech | 2025-10-24 | 2025-10-24 | Yes | Dirty Mid Coupler | Yes
2025-10-21 | Lawley | Resolved | FT394187 | DR1751662 | Connectivity | Velocity MNT Tech | 2025-10-27 | 2025-10-27 | Yes | No Issue found | Yes
2025-10-21 | Lawley | Resolved | FT398998 | DR1750881 | Connectivity | Velocity MNT Tech | 2025-10-30 | 2025-10-31 | Yes | No Fault Found | Yes
2025-11-03 | Lawley | Resolved | FT329654 | DR1751280 | No Category | Velocity MNT Tech | 2025-11-04 | 2025-11-06 |  | New HD Cable to be installed | Yes
2025-11-03 | Lawley | Resolved | FT437119 | DR1748376 | Connnectivity | Velocity MNT Tech | 2025-11-04 | 2025-11-04 | Yes | Dirty Midcoupler | Yes
2025-11-04 | Mohadin | Resolved | FT413370 | DR1853768 | Connectivity | Velocity MNT Tech | 2025-11-10 | 2025-11-10 | Yes | No Fault Found | Yes
2025-11-04 | Lawley | Resolved | FT415994 | DR1750463 | Connectivity | Velocity MNT Tech | 2025-11-04 | 2025-11-06 |  | New HD Cable to be installed | Yes
2025-11-04 | Lawley | Resolved | FT424375 | DR1748710 | Connectivity | Velocity MNT Tech | 2025-11-04 | 2025-11-04 | Yes | Traced fault to FJ - Recoiled and Respliced to restore | Yes
2025-11-04 | Lawley | Resolved | FT429822 | DR1753151 | Connectivity | Velocity MNT Tech | 2025-11-04 | 2025-11-04 | Yes | Reseated Midcoupler / Loose Connection | Yes
2025-11-10 | Lawley | Resolved | FT454139 | DR1732121 | Connectivity | Velocity MNT Tech | 2025-11-14 | 2025-11-14 |  | Reconnected in SJC | Yes
2025-11-10 | Mohadin | Resolved | FT452179 | DR1856977 | Connectivity | Velocity MNT Tech | 2025-11-10 | 2025-11-10 |  | Activations to activate device. Submitted to Activations team | Yes
2025-11-10 | Lawley | Resolved | FT452295 | DR1749903 | Connectivity | Velocity MNT Tech | 2025-11-14 | 2025-11-14 |  | No Fault Found | Yes
2025-11-10 | Lawley | Resolved | FT455541 | DR1750324 | Connectivity | Velocity MNT Tech | 2025-11-11 | 2025-11-29 |  | Activated. DR and SN are different. FT Updated | Yes
2025-11-10 | Mohadin | Resolved | FT410148 | DR1853877 | Connectivity | Velocity MNT Tech | 2025-11-11 | 2025-11-12 | Yes | Dirty MC - Cleaned Restored | Yes
2025-11-10 | Mohadin | Resolved | FT410375 | DR1853702 | Connectivity | Velocity MNT Tech | 2025-11-11 | 2025-11-12 | Yes | No Fault Found | Yes
2025-11-10 | Mohadin | Resolved | FT410860 | DR1853707 | Connectivity | Velocity MNT Tech | 2025-11-11 | 2025-11-12 | Yes | Rebooted Device | Yes
2025-11-10 | Mohadin | Resolved | FT411028 | DR1853751 | Connectivity | Velocity MNT Tech | 2025-11-11 | 2025-11-12 | Yes | No Fault Found | Yes
2025-11-10 | Mohadin | Resolved | FT411128 | DR1853705 | Connectivity | Velocity MNT Tech | 2025-11-13 | 2025-11-13 |  | Rebooted Device | Yes
2025-11-10 | Mohadin | Resolved | FT411779 | DR1853874 | Connectivity | Velocity MNT Tech | 2025-11-13 | 2025-11-13 |  | No Fault Found | Yes
2025-11-10 | Mohadin | Resolved | FT411916 | DR1853557 | Connectivity | Velocity MNT Tech | 2025-11-13 | 2025-11-13 |  | No Fault Found | Yes
2025-11-10 | Lawley | Resolved | FT411960 | DR1752532 | Connectivity | Velocity MNT Tech | 2025-11-11 | 2025-11-18 | Yes | No Fault Found | Yes
2025-11-10 | Mohadin | Resolved | FT411979 | DR1853709 | Connectivity | Velocity MNT Tech | 2025-11-13 | 2025-11-26 |  | No Fault Found | Yes
2025-11-10 | Mohadin | Resolved | FT412196 | DR1853894 | Connectivity | Velocity MNT Tech | 2025-11-13 | 2025-11-13 |  | Patch lead was unplugged | Yes
2025-11-10 | Mohadin | Resolved | FT413873 | DR1854672 | Connectivity | Velocity MNT Tech | 2025-11-13 | 2025-11-13 |  | No Fault Found | Yes
2025-11-10 | Lawley | Resolved | FT427748 | DR1748516 | Connectivity | Velocity MNT Tech | 2025-11-11 | 2025-11-13 |  | No Fault Found | Yes
2025-11-10 | Mamelodi | Resolved | FT430164 | No DR Supplied | Property Damage | Velocity MNT Tech | 2025-11-10 | 2025-11-11 |  | The issue reported has been rectified | Yes
2025-11-10 | Mohadin | Resolved | FT432588 | DR1854255 | Connectivity | Velocity MNT Tech | 2025-11-13 | 2025-11-26 |  | Cleaned Mid Coupler, Light Levels improved | Yes
2025-11-10 | Mohadin | Resolved | FT434294 | DR1854148 | Connectivity | Velocity MNT Tech | 2025-11-13 | 2025-11-29 |  | Client does not exist on Master OES. Cannot conduct basic FLC | Yes
2025-11-10 | Lawley | Resolved | FT439273 | DR1752532 | Connectivity | Velocity MNT Tech | 2025-11-11 | 2025-11-18 | Yes | No Fault Found | Yes
2025-11-10 | Lawley | Resolved | FT440057 | DR1748705 | Connectivity | Velocity MNT Tech | 2025-11-11 | 2025-11-13 |  | No Fault Found | Yes
2025-11-10 | Lawley | Resolved | FT440503 | DR1748669 | Connectivity | Velocity MNT Tech | 2025-11-11 | 2025-11-13 |  | No Fault Found | Yes
2025-11-10 | Mohadin | Resolved | FT440893 | DR1856904 | Connectivity | Velocity MNT Tech | 2025-11-13 | 2025-11-29 |  | Client does not exist on Master OES. Cannot conduct basic FLC | Yes
2025-11-10 | Mohadin | Resolved | FT440912 | DR1856904 | Connectivity | Velocity MNT Tech | 2025-11-13 | 2025-11-29 |  | Client does not exist on Master OES. Cannot conduct basic FLC | Yes
2025-11-10 | Mohadin | Resolved | FT441739 | DR1854255 | Connectivity | Velocity MNT Tech | 2025-11-13 | 2025-11-26 |  | Cleaned Mid Coupler, Light Levels improved | Yes
2025-11-10 | Lawley | Resolved | FT442865 | DR1751460 | ONT Move | Velocity MNT Tech | 2025-11-14 | 2025-11-14 |  | Rebooted Device | Yes
2025-11-10 | Mohadin | Resolved | FT444226 | DR1854800 | Connectivity | Velocity MNT Tech | 2025-11-13 | 2025-11-27 |  | Loose Connection in SJC. Reseated and resolved | Yes
2025-11-10 | Mohadin | Resolved | FT448787 | DR1854800 | Connectivity | Velocity MNT Tech | 2025-11-13 | 2025-11-27 |  | Loose Connection in SJC. Reseated and resolved | Yes
2025-11-10 | Mohadin | Resolved | FT451682 | DR1854735 | Connectivity | Velocity MNT Tech | 2025-11-13 | 2025-11-13 | Yes | Device was off. Switched Device on | Yes
2025-11-13 | Mohadin | Resolved | FT458266 | DR1853456 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | ONT RX Levels are Perfect. NOC to conduct FLC | Yes
2025-11-13 | Lawley | Resolved | FT462215 | DR1748444 | Connectivity | Velocity MNT Tech | 2025-11-14 | 2025-11-18 |  | Respliced at Splitter | Yes
2025-11-13 | Lawley | Resolved | FT462624 | DR1732117 | Connectivity | Velocity MNT Tech | 2025-11-14 | 2025-11-14 |  | Cable was damaged, pulled in new cable | Yes
2025-11-14 | Mohadin | Resolved | FT466659 | DR1854041 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-12-05 |  | Cleaned connectors in SJC. High Readings | Yes
2025-11-14 | Mohadin | Resolved | FT466632 | DR1853707 | Connectivity | Velocity MNT Tech | 2025-11-14 | 2025-11-14 | Yes | Ticket was resolved on the 2025/11/12 under FT410860 | Yes
2025-11-14 | Mohadin | Resolved | FT458499 | DR1857068 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-12-01 |  | Current ONT RX in range as per Master OES. NOC to conduct FLC | Yes
2025-11-14 | Mohadin | Resolved | FT455969 | DR1854759 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-12-05 |  | To be investigate -40 / ONT Link light flashing on investigation. Reactivated | Yes
2025-11-17 | Lawley | Resolved | FT478519 | DR1748548 | Connectivity | Velocity MNT Tech | 2025-11-17 | 2025-11-18 |  | Respliced 1:8 Way Splitter | Yes
2025-11-17 | Lawley | Resolved | FT478181 | DR1750900 | Connectivity | Velocity MNT Tech | 2025-11-17 | 2025-11-20 |  | Redid Cable Manangement | Yes
2025-11-17 | Mohadin | Resolved | FT476984 | DR1853477 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-12-05 |  | Link light flashing on investigation. Reactivated device. | Yes
2025-11-17 | Mohadin | Resolved | FT470501 | DR1853883 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-12-05 |  | Current ONT RX in range as per Master OES. NOC to conduct FLC | Yes
2025-11-19 | Lawley | Resolved | FT477511 | DR1748451 | Connectivity | Velocity MNT Tech | 2025-11-19 | 2025-11-19 |  |  | Yes
2025-11-19 | Mohadin | Resolved | FT466529 | DR1853532 | Connectivity | Velocity MNT Tech | 2025-11-27 |  |  | Current ONT RX in range as per Master OES. NOC to conduct FLC | Yes
2025-11-19 | Mohadin | Resolved | FT469708 | DR1857279 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-12-08 |  | Link was not Live. Resplicing done at the SJC | Yes
2025-11-19 | Mohadin | Resolved | FT470242 | DR1857318 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-29 |  | Current ONT RX Levels are in range. NOC to complete FLC with Client | Yes
2025-11-19 | Lawley | Resolved | FT471675 | DR1751733 | Connectivity | Velocity MNT Tech | 2025-11-19 | 2025-11-19 |  | Patched at SJC | Yes
2025-11-19 | Mohadin | Resolved | FT473045 | DR1854477 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | No Fault Found | Yes
2025-11-19 | Mohadin | Resolved | FT478377 | DR1857318 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-29 |  | High Readings at the ONT, Cleaning of Connectors at SJC. | Yes
2025-11-19 | Lawley | Resolved | FT479589 |  | Connectivity | Velocity MNT Tech | 2025-11-19 | 2025-11-19 |  | Sent to Activations Team to complete | Yes
2025-11-19 | Mohadin | Resolved | FT479773 | DR1854348 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-19 | Mohadin | Resolved | FT480074 | DR1854617 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-19 | Mohadin | Resolved | FT480148 | DR1853711 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-19 | Mohadin | Resolved | FT481651 | DR1853949 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-19 | Mohadin | Resolved | FT483070 | DR1853929 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-12-05 |  | Current ONT RX in range as per Master OES. NOC to conduct FLC | Yes
2025-11-19 | Mohadin | Resolved | FT483332 | DR1853705 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT Rx within Range as per Master OES. NOC to FLC | Yes
2025-11-19 | Mohadin | Resolved | FT483475 | DR1856881 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT Rx within Range as per Master OES. NOC to FLC | Yes
2025-11-19 | Mohadin | Resolved | FT484081 | DR1857155 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-12-23 | Yes | Completed through splicing in SJC to make Link Live. | Yes
2025-11-25 | Lawley | Resolved | FT513159 | DR1734543 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-25 | Lawley | Resolved | FT512653 | DR1753200 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-25 | Lawley | Resolved | FT512047 | DR1734543 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-25 | Lawley | Resolved | FT511941 | DR1734906 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-25 | Lawley | Resolved | FT511572 | DR1753125 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-25 | Lawley | Resolved | FT511506 | DR1751449 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-25 | Lawley | Resolved | FT511200 | DR1753054 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-25 | Lawley | Resolved | FT510686 | DR1749896 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-25 | Mohadin | Resolved | FT510230 | DR1853430 | Connectivity | Velocity MNT Tech | 2025-11-25 | 2025-11-27 |  | Device Rebooted | Yes
2025-11-25 | Lawley | Resolved | FT509000 | DR1748345 | Connectivity | Velocity MNT Tech | 2025-11-25 | 2025-11-25 |  | Rebooted Device | Yes
2025-11-25 | Lawley | Resolved | FT508975 | DR1733377 | Connectivity | Velocity MNT Tech | 2025-11-25 | 2025-11-25 |  | Bend in cable caused light loss, rectified | Yes
2025-11-25 | Lawley | Resolved | FT507066 | DR1733579 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-25 | Lawley | Resolved | FT507039 | DR1752884 | Connectivity | Velocity MNT Tech | 2025-11-25 | 2025-11-25 |  | Homedrop Cable Replaced | Yes
2025-11-25 | Lawley | Resolved | FT506844 | DR1733377 | Connectivity | Velocity MNT Tech | 2025-11-25 | 2025-11-25 |  | Bend in cable caused light loss, rectified | Yes
2025-11-25 | Lawley | Resolved | FT506754 | DR1753035 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-25 | Lawley | Resolved | FT506732 | DR1748700 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-25 | Lawley | Resolved | FT506728 | DR1752455 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-25 | Lawley | Resolved | FT506382 | DR1734631 | Connectivity | Velocity MNT Tech | 2025-11-25 | 2025-11-25 |  | Device Rebooted | Yes
2025-11-25 | Mohadin | Resolved | FT506376 | DR1853430 | Connectivity | Velocity MNT Tech | 2025-11-25 | 2025-11-27 |  | Device Rebooted | Yes
2025-11-25 | Mohadin | Resolved | FT506045 | DR1856977 | Connectivity | Velocity MNT Tech |  |  |  | ONT RX as per Master OES Current Active | Yes
2025-11-25 | Lawley | Resolved | FT505838 | DR1750168 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-25 | Mohadin | Resolved | FT505765 | DR1853737 | Connectivity | Velocity MNT Tech | 2025-11-26 | 2025-11-27 |  | No Fault Found | Yes
2025-11-25 | Lawley | Resolved | FT505758 | DR1749867 | Connectivity | Velocity MNT Tech | 2025-11-25 | 2025-12-02 |  | Low power levels caused by kinked cable inside ceiling. Stretched cable. | Yes
2025-11-25 | Lawley | Resolved | FT505570 | DR1752969 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-25 | Lawley | Resolved | FT505426 | DR1734889 | Connectivity | Velocity MNT Tech | 2025-11-25 | 2025-11-25 |  | Device Rebooted | Yes
2025-11-25 | Lawley | Resolved | FT503311 | DR1748545 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-25 | Lawley | Resolved | FT503130 | DR1748459 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-25 | Lawley | Resolved | FT503099 | DR1752505 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-25 | Mamelodi | Resolved | FT500970 | DR470331 | Connectivity | Velocity MNT Tech |  | 2025-12-22 | Yes | No Issues Found. Power Meter Readings are Normal. | No
2025-11-25 | Lawley | Resolved | FT499061 | DR1748438 | Property Damage | Velocity MNT Tech |  | 2025-12-25 | Yes | HD to be replaced. Damaged Drop Cable was Replaced | Yes
2025-11-25 | Mohadin | Resolved | FT498769 | DR1854247 | Connectivity | Velocity MNT Tech | 2025-11-26 | 2025-11-27 |  | No Fault Found. Customer was affected by outage | Yes
2025-11-25 | Mohadin | Resolved | FT496790 | DR1853804 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT Rx within Range as per Master OES. NOC to FLC | Yes
2025-11-25 | Mohadin | Resolved | FT490441 | DR1853428 | Connectivity | Velocity MNT Tech | 2025-11-27 |  |  | No Fault Found. DR is also incorrect. Phoned Client and stated they are Connected | Yes
2025-11-25 | Mohadin | Resolved | FT488695 | DR1857348 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-12-09 | Yes | No Issues Found. Power Meter Readings are Normal. | Yes
2025-11-25 | Mohadin | Resolved | FT488152 | DR1857318 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-29 |  | High Readings at the ONT, Cleaning of Connectors at SJC. | Yes
2025-11-25 | Lawley | Resolved | FT487200 | DR1734546 | Connectivity | Velocity MNT Tech | 2025-11-25 | 2025-12-02 |  | Faulty Device. Swapped out old device | Yes
2025-11-25 | Mohadin | Resolved | FT458452 | DR1853456 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | ONT RX Levels are Perfect. NOC to conduct FLC | Yes
2025-11-25 | Mamelodi | Resolved | FT454332 | DR471335 | Connectivity | Velocity MNT Tech | 2025-12-01 | 2025-12-01 |  | No Fault Found | Yes
2025-11-25 | Mohadin | Resolved | FT459295 |  | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Sent to Activations to resolve | Yes
2025-11-25 | Mohadin | Resolved | FT469845 | DR1854455 | Connectivity | Velocity MNT Tech | 2025-11-25 | 2025-11-25 |  | Services restored after damages repaired caused by SMME | Yes
2025-11-25 | Mohadin | Resolved | FT481603 | DR1857321 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-12-01 |  | Current ONT RX in range as per Master OES. NOC to conduct FLC | Yes
2025-11-25 | Mohadin | Resolved | FT483139 | DR1857681 | Connectivity | Velocity MNT Tech | 2025-11-25 | 2025/11/2025 |  | No Fault Found | Yes
2025-11-25 | Mohadin | Resolved | FT490157 | DR1854545 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per OES is within range and client active | Yes
2025-11-25 | Mamelodi | Resolved | FT502293 | DR470456 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-12-01 |  | No Fault Found | Yes
2025-11-25 | Lawley | Resolved | FT504858 | DR1748523 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-25 | Mamelodi | Resolved | FT505084 | DR471390 | ONT Move | Velocity MNT Tech | 2025-12-01 | 2025-12-01 |  | Client advised to install extenders in the house | Yes
2025-11-25 | Mohadin | Resolved | FT506040 | DR1853877 | Connectivity | Velocity MNT Tech | 2025-11-25 | 2025-11-27 |  | Device Rebooted | Yes
2025-11-25 | Lawley | Resolved | FT513074 | DR1752757 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-26 | Lawley | Resolved | FT514946 | DR1752480 | Connectivity | Velocity MNT Tech | 2025-11-27 | 2025-11-27 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-11-29 | Lawley | Resolved | FT510444 | DR1734631 | Connectivity | Velocity MNT Tech | 2025-11-29 | 2025-11-29 |  | No Fault Found | Yes
2025-11-29 | Lawley | Resolved | FT513635 | DR1751274 | Connectivity | Velocity MNT Tech | 2025-11-29 | 2025-11-29 |  | Reconnected at SJC and resolved | Yes
2025-11-29 | Lawley | Resolved | FT513948 | DR1751815 | Connectivity | Velocity MNT Tech | 2025-11-29 |  |  |  | Yes
2025-11-29 | Lawley | Resolved | FT516987 | DR1752683 | Connectivity | Velocity MNT Tech | 2025-11-29 | 2025-11-29 |  | No Fault Found | Yes
2025-11-29 | Lawley | Resolved | FT517443 | DR1748824 | Connectivity | Velocity MNT Tech | 2025-11-29 | 2025-11-29 |  | Low Light Levels. Cleaned Mid Coupler. Resolved | Yes
2025-11-29 | Lawley | Resolved | FT517723 | DR1732117 | Connectivity | Velocity MNT Tech | 2025-11-29 | 2025-11-29 |  | Low Levels. Reptached. Resolved | Yes
2025-12-01 | Mohadin | Resolved | FT525822 | DR1853482 | Connectivity | Velocity MNT Tech | 2025-12-04 | 2025-12-04 |  | Link light flashing. Reactivated the device | Yes
2025-12-01 | Mohadin | Resolved | FT523509 | DR1853904 | Connectivity | Velocity MNT Tech | 2025-12-04 | 2025-12-04 |  | Link light flashing. Cleaned dirty Midcoupler. Reactivated Device | Yes
2025-12-01 | Lawley | Resolved | FT519697 | DR1751832 | Connectivity | Velocity MNT Tech | 2025-12-01 | 2025-12-02 |  | Low Levels. Feeder to Splitter was broken in one of the loops. | Yes
2025-12-01 | Lawley | Resolved | FT519005 | DR1734104 | Connectivity | Velocity MNT Tech | 2025-12-01 | 2025-12-02 |  | Low Levels. Repatched Cable | Yes
2025-12-01 | Lawley | Resolved | FT518536 | DR1734687 | Connectivity | Velocity MNT Tech | 2025-12-01 | 2025-12-01 |  | No Fault Found | Yes
2025-12-01 | Mohadin | Resolved | FT517186 | DR1853384 | Connectivity | Velocity MNT Tech | 2025-12-04 | 2025-12-04 |  | Dirty Midcoupler | Yes
2025-12-01 | Lawley | Resolved | FT516804 | DR1751562 | Connectivity | Velocity MNT Tech | 2025-12-01 | 2025-12-10 | Yes | Device was Faulty. Swapped out ONT. | Yes
2025-12-01 | Lawley | Resolved | FT516480 | DR1732185 | Connectivity | Velocity MNT Tech | 2025-12-01 | 2025-12-01 |  | Cleaned Mid Coupler - Services Restored | Yes
2025-12-01 | Lawley | Resolved | FT515734 | DR1732210 | Connectivity | Velocity MNT Tech | 2025-12-01 | 2025-12-01 |  | No Fault Found - Rebooted Device | Yes
2025-12-01 | Lawley | Resolved | FT515581 | DR1752532 | Connectivity | Velocity MNT Tech | 2025-12-01 | 2025/1205 | Yes | Current ONT RX in range as per Master OES. NOC to conduct FLC | Yes
2025-12-01 | Mohadin | Resolved | FT514792 | DR1857318 | Connectivity | Velocity MNT Tech | 2025-12-01 | 2025-12-01 |  | Current ONT RX as per Master OES in range. NOC to Complete FLC | Yes
2025-12-01 | Lawley | Resolved | FT510913 | DR1751815 | Connectivity | Velocity MNT Tech | 2025-12-02 |  |  |  | Yes
2025-12-01 | Lawley | Resolved | FT514315 | DR1734352 | Connectivity | Velocity MNT Tech | 2025-12-02 | 2025-12-02 |  | Cable Connectors were dirty causing low power levels. Cleaned the connector | Yes
2025-12-01 | Lawley | Resolved | FT514180 | DR1734460 | Connectivity | Velocity MNT Tech | 2025-12-02 | 2025-12-02 |  | Low Levels. The feeder to a splitter was broken in one of the loops. | Yes
2025-12-01 | Lawley | Resolved | FT513833 | DR1752620 | Connectivity | Velocity MNT Tech | 2025-12-02 | 2025-12-02 |  | Customer not home, but confirmed fibre is working. | Yes
2025-12-01 | Lawley | Resolved | FT513743 | DR1734460 | Connectivity | Velocity MNT Tech | 2025-12-02 | 2025-12-02 |  | Low Levels. The feeder to a splitter was broken in one of the loops. | Yes
2025-12-01 | Lawley | Resolved | FT512921 | DR1752532 | Connectivity | Velocity MNT Tech | 2025-12-02 | 2025-12-05 | Yes | Current ONT RX in range as per Master OES. NOC to conduct FLC | Yes
2025-12-01 | Lawley | Resolved | FT512883 | DR1749852 | Connectivity | Velocity MNT Tech | 2025-12-02 | 2025-12-02 |  | No Fault Found. | Yes
2025-12-01 | Lawley | Resolved | FT512573 | DR1752067 | Connectivity | Velocity MNT Tech | 2025-12-02 | 2025-12-02 |  | No Fault Found. | Yes
2025-12-02 | Lawley | Resolved | FT524195 | DR1750682 | Connectivity | Velocity MNT Tech | 2025-12-02 | 2025-12-02 |  | No Fault Found. | Yes
2025-12-02 | Mohadin | Resolved | FT532557 | DR1857408 | Connectivity | Velocity MNT Tech | 2025-12-02 | 2025-12-02 |  | Information given incorrect. FT NOC to submit proper ticket | Yes
2025-12-02 | Lawley | Resolved | FT534220 | DR1748813 | Connectivity | Velocity MNT Tech | 2025-12-02 | 2025-12-03 |  | Low Power Levels. Cable was not plugged at the wall. | Yes
2025-12-03 | Lawley | Resolved | FT526643 | DR1752141 | Connectivity | Velocity MNT Tech | 2025-12-04 | 2024-12-05 |  | Low power levels caused by loose connection at the pole | Yes
2025-12-03 | Lawley | Resolved | FT493433 | DR1733442 | Connectivity | Velocity MNT Tech | 2024-12-04 | 2025-12-04 |  | No Issue found | Yes
2025-12-03 | Lawley | Resolved | FT534969 | DR1748345 | Connectivity | Velocity MNT Tech | 2025-12-04 | 2025-12-05 |  | Pon was down and caused low power levels. Respliced broken Fibre | Yes
2025-12-03 | Mohadin | Resolved | FT534874 | DR1853949 | Connectivity | Velocity MNT Tech | 2025-12-04 | 2024-12-04 | 2024-12-04 | Link light was flashing on ivestigation. Reactivated the Device. | Yes
2025-12-03 | Lawley | Resolved | FT534128 | DR1733782 | Connectivity | Velocity MNT Tech | 2025-12-04 | 2025-12-04 |  | No issue Found. Device was not activated | Yes
2025-12-03 | Lawley | Resolved | FT534073 | DR1732087 | Connectivity | Velocity MNT Tech | 2025-12-04 | 2025-12-12 |  | Client was not available. Customer confirmed that Internet is working | Yes
2025-12-03 | Lawley | Resolved | FT523261 | DR1750740 | Connectivity | Velocity MNT Tech | 2025-12-04 |  |  | Fibre was broken. Respliced to restore connection. | Yes
2025-12-03 | Mohadin | Resolved | FT517005 | DR1853562 | Connectivity | Velocity MNT Tech | 2025-12-04 | 2025-12-04 | Yes | Link light flashing. Reactivated on Device. | Yes
2025-12-03 | Mohadin | Resolved | FT536825 | DR142077 | Property Damage | Velocity MNT Tech | 2025-12-03 | 2025-12-03 |  | Ticket information incorrect. Not Velocity Built site. | Yes
2025-12-03 | Lawley | Resolved | FT534791 | DR1748562 | Connectivity | Velocity MNT Tech | 2025-12-04 | 2024-12-04 |  | Low power levels caused by loose connection at the pole. | Yes
2025-12-04 | Lawley | Resolved | FT532441 | DR1732087 | Connectivity | Velocity MNT Tech | 2025-12-04 | 2025-12-05 |  | Client stated they have Internet can close ticket
2025-12-04 | Mohadin | Resolved | FT538846 | DR1853564 | Connectivity | Velocity MNT Tech | 2025-12-05 | 2025-12-05 |  | Link light flashing. Reactivated device. | Yes
2025-12-05 | Mohadin | Resolved | FT541035 | DR1856977 | Connectivity | Velocity MNT Tech | 2025-12-05 | 2025-12-08 |  | Faulty (ONT Swop) Done. | Yes
2025-12-05 | Mohadin | Resolved | FT541215 | DR1854718 | Connectivity | Velocity MNT Tech | 2025-12-05 | 2025-12-08 |  | Connector cleaned. Improved Power Meter Readings. ONT RX within Budgeted Rage | Yes
2025-12-05 | Mohadin | Resolved | FT539067 | DR142077 | Connectivity | Velocity MNT Tech | 2025-12-05 | 2025-12-08 |  | Confirmed not a client in Mohadin | Yes
2025-12-05 | Mohadin | Resolved | FT541162 | DR1855328 | Connectivity | Velocity MNT Tech | 2025-12-08 | 2025-12-08 |  | High Readings at the ONT, Cleaning of Connectors at SJC. | Yes
2025-12-08 | Mohadin | Resolved | FT541917 | DR1855297 | Connectivity | Velocity MNT Tech | 2025-12-08 | 2025-12-09 |  | No Issue Found | Yes
2025-12-08 | Mohadin | Resolved | FT543403 | DR1855297 | Connectivity | Velocity MNT Tech | 2025-12-08 | 2025-12-09 |  | No Issue Found | Yes
2025-12-08 | Lawley | Resolved | FT543083 | DR1751847 | Connectivity | Velocity MNT Tech | 2025-12-08 | 2025-12-10 | Yes | Homedrop Cable Replaced | Yes
2025-12-08 | Lawley | Resolved | FT542520 | DR1729521 | Connectivity | Velocity MNT Tech | 2025-12-08 | 2025-12-10 | Yes | Poor Coiling of Cable caused low power levels. Recoiling Recovering. Power Levels Improved. | Yes
2025-12-08 | Lawley | Resolved | FT542473 | DR1729521 | Connectivity | Velocity MNT Tech | 2025-12-08 | 2025-12-10 | Yes | Poor Coiling of Cable caused low power levels. Recoiling Recovering. Power Levels Improved. | Yes
2025-12-08 | Mohadin | Resolved | FT543127 | DR1857363 | Connectivity | Velocity MNT Tech | 2025-12-08 | 2025-12-08 | Yes | No Fault Found | Yes
2025-12-08 | Mamelodi | Resolved | FT544681 | DR471279 | Connectivity | Velocity MNT Tech | 2025-12-08 | 2025-12-22 | Yes | Cleaned Dirty connection point in SJC. Light levels Improved. | Yes
2025-12-08 | Mohadin | Resolved | FT546183 | DR1855582 | Connectivity | Velocity MNT Tech | 2025-12-08 | 2025-12-09 | Yes | Activations not Completed. MNT Completed Activation | Yes
2025-12-08 | Mohadin | Resolved | FT546481 | DR1855582 | Connectivity | Velocity MNT Tech | 2025-12-08 | 2025-12-09 | Yes | Activations not Completed. MNT Completed Activation | Yes
2025-12-08 | Mohadin | Resolved | FT540684 | DR1857589 | Connectivity | Velocity MNT Tech | 2025-12-08 | 2025-12-09 | Yes | Respliced at SJC to change Link status to Live. | Yes
2025-12-08 | Mohadin | Resolved | FT541248 | DR1856908 | Property Damage | Velocity MNT Tech | 2025-12-08 | 2025-12-10 | Yes | No Fault Found. Clients TV not Compatible does not have chrome. | Yes
2025-12-08 | Mohadin | Resolved | FT549650 | DR1853572 | Connectivity | Velocity MNT Tech | 2025-12-08 | 2025-12-20 | Yes | SJC is Live. | Yes
2025-12-08 | Mohadin | Resolved | FT543284 | DR1853572 | Connectivity | Velocity MNT Tech | 2025-12-08 | 2025-12-20 | Yes | SJC is Live. | Yes
2025-12-08 | Lawley | Resolved | FT549468 | DR1734844 | Connectivity | Velocity MNT Tech | 2025-12-08 | 2025-12-12 | yes | Faulty Splitter. Respliced & Restored | Yes
2025-12-09 | Mohadin | Resolved | FT543379 | DR1853760 | Connectivity | Velocity MNT Tech | 2025-12-10 | 2025-12-10 | Yes | Seated Connector correctly. Services Restored | Yes
2025-12-09 | Lawley | Resolved | FT550086 | DR1751732 | Connectivity | Velocity MNT Tech | 2025-12-10 | 2025-12-10 | Yes | Cleaned Dirty connection point in SJC. Light levels Improved. | Yes
2025-12-09 | Lawley | Resolved | FT550473 | DR1734844 | Connectivity | Velocity MNT Tech | 2025-12-08 | 2025-12-12 | Yes | faulty Splitter. In pliced & In toind | Yes
2025-12-09 | Lawley | Resolved | FT551966 | DR1753207 | Connectivity | Velocity MNT Tech | 2025-12-10 | 2025-12-11 | Yes | ONT Not Activated. Services Activated & Restored. | Yes
2025-12-09 | Lawley | Resolved | FT513636 | DR1733288 | Connectivity | Velocity MNT Tech | 2025-12-10 | 2025-12-18 | Yes | Respliced leg on 1:8 Way Splitter | Yes
2025-12-09 | Mohadin | Resolved | FT548220 | DR1855362 | Connectivity | Velocity MNT Tech | 2025-12-10 | 2025-12-23 | Yes | Respliced leg in CMJ. | Yes
2025-12-09 | Lawley | Resolved | FT524741 | DR1748420 | Connectivity | Velocity MNT Tech | 2025-12-10 | 2025-12-12 | Yes | ONT was down due to a Faulty Power Adapter | Yes
2025-12-09 | Mohadin | Resolved | FT552921 | DR1857408 | Connectivity | Velocity MNT Tech | 2025-12-10 | 2025-12-29 | Yes | Completed throuh Splicing in SJC. | Yes
2025-12-09 | Mohadin | Resolved | FT552904 | DR1857408 | Connectivity | Velocity MNT Tech | 2025-12-10 | 2025-12-29 | Yes | Completed throuh Splicing in SJC. | Yes
2025-12-09 | Lawley | Resolved | FT551161 | DR1734844 | Connectivity | Velocity MNT Tech | 2025-12-10 | 2025-12-22 | Yes | Faulty Splitter, Respliced and Restored. DR Typing Error | Yes
2025-12-09 | Lawley | Resolved | FT539713 | DR1733435 | Connectivity | Velocity MNT Tech | 2025-12-10 | 2025-12-12 | Yes | Faulty Drop Cable. New Drop Cable was installed. | Yes
2025-12-09 | Mohadin | Resolved | FT552388 | DR1853653 | Connectivity | Velocity MNT Tech | 2025-12-10 | 2025-12-10 | Yes | ONT Not Activated. Services Activated & Restored. | Yes
2025-12-09 | Mohadin | Resolved | FT549518 | DR1856833 | Connectivity | Velocity MNT Tech | 2025-12-10 | 2025-12-10 | Yes | No Issues Found. Power Meter Readings are Normal. | Yes
2025-12-09 | Mohadin | Resolved | FT554063 | DR1853602 | Connectivity | Velocity MNT Tech | 2025-12-10 | 2025-12-10 | Yes | Connector cleaned. Improved Power Meter Readings. ONT RX within Budgeted Rage | Yes
2025-12-09 | Mohadin | Resolved | FT545336 | DR1857408 | Connectivity | Velocity MNT Tech | 2025-12-10 | 2025-12-29 | Yes | Completed throuh Splicing in SJC. | Yes
2025-12-09 | Lawley | Resolved | FT549763 | DR1729521 | Connectivity | Velocity MNT Tech | 2025-12-10 | 2025-12-10 | Yes | Poor Coiling of Cable caused low power levels. Recoiling Recovering. Power Levels Improved. | Yes
2025-12-09 | Lawley | Resolved | FT548129 | DR1734704 | Connectivity | Velocity MNT Tech | 2025-12-10 | 2025-12-10 | Yes | Vandalism - Replace Home Drop | Yes
2025-12-10 | Mohadin | Resolved | FT553958 | DR1856857 | Connectivity | Velocity MNT Tech | 2025-12-10 | 2025-12-11 | Yes | Completed through splicing in SJC. | Yes
2025-12-10 | Lawley | Resolved | FT549330 | DR1733834 | Connectivity | Velocity MNT Tech | 2025-12-11 | 2025-12-11 | Yes | ONT Reactivated was in Locked Mode | Yes
2025-11-11 | Lawley | Resolved | FT538616 | DR1748376 | Connectivity | Velocity MNT Tech | 2025-12-11 | 2025-12-11 | Yes | No Access. Phoned Client and she stated her Internet was down and working again. Close ticket | Yes
2025-12-11 | Lawley | Resolved | FT560181 | DR1733191 | Connectivity | Velocity MNT Tech | 2025-12-12 | 2025-12-29 | Yes | Dropcable damaged due to ceiling Rats. | Yes
2025-12-11 | Mohadin | Resolved | FT563880 | DR1854278 | Connectivity | Velocity MNT Tech | 2025-12-11 | 2025-12-12 | Yes | No Fault Found. Client logged a call when Internet was down. | Yes
2025-12-11 | Mohadin | Resolved | FT564308 | DR1855553 | Connectivity | Velocity MNT Tech | 2025-12-11 | 2025-12-12 | Yes | No Fault Found. Client logged a call when Internet was down. | Yes
2025-12-11 | Mohadin | Resolved | FT562341 | DR1857712 | Connectivity | Velocity MNT Tech | 2025-12-11 | 2025-12-12 | Yes | No Fault Found. Client logged a call when Internet was down. | Yes
2025-12-11 | Lawley | Resolved | FT558810 | DR1750753 | Connectivity | Velocity MNT Tech | 2025-12-12 | 2025-12-12 | Yes | Device Reactivated | Yes
2025-12-11 | Lawley | Resolved | FT566880 | DR1733824 | Connectivity | Velocity MNT Tech | 2025-12-12 | 2025-12-18 | Yes | Client stated they have Internet can close ticket | Yes
2025-12-15 | Mohadin | Resolved | FT538730 | DR1853877 | Connectivity | Velocity MNT Tech | 2025-12-15 | 2025-12-17 | Yes | Current ONT RX in range as per Master OES. No Issues Found. Network was down. | Yes
2025-12-15 | Lawley | Resolved | FT567090 | DR1734953 | Connectivity | Velocity MNT Tech | 2025-12-15 | 2025-12-19 | Yes | Low Power Levels due to Faulty Home Drop and Dirty Midcoupler | Yes
2025-12-15 | Mohadin | Resolved | FT567820 | DR1857543 | Connectivity | Velocity MNT Tech | 2025-12-15 | 2025-12-17 | Yes | Current ONT RX in range as per Master OES. Duplicate | Yes
2025-12-15 | Lawley | Resolved | FT568405 | DR1752278 | Connectivity | Velocity MNT Tech | 2025-12-15 | 2025-12-19 | Yes | Faulty Device. Swapped out old device (Customer has 2 Routers) | Yes
2025-12-15 | Mohadin | Resolved | FT571041 | DR1857337 | Connectivity | Velocity MNT Tech | 2025-12-15 | 2025-12-29 | Yes | Completed through Splicing in the SJC. | Yes
2025-12-15 | Lawley | Resolved | FT569579 | DR1733303 | Connectivity | Velocity MNT Tech | 2025-12-15 | 2025-12-15 | Yes | Fibre Damaged and was Respliced. Services Restored. | Yes
2025-12-15 | Lawley | Resolved | FT573105 | DR1733303 | Connectivity | Velocity MNT Tech | 2025-12-15 | 2025-12-17 | Yes | Fibre Damaged and was Respliced. Services Restored.
2025-12-15 | Lawley | Resolved | FT568198 | DR1752683 | Connectivity | Velocity MNT Tech | 2025-12-15 | 2025-12-15 | Yes | Current ONT RX in range as per Master OES. | Yes
2025-12-15 | Mohadin | Resolved | FT573587 | DR1857543 | Connectivity | Velocity MNT Tech | 2025-12-15 | 2025-12-17 | Yes | Connector was not plugged in correctly. Services Restored. | Yes
2025-12-15 | Mohadin | Resolved | FT560792 | DR1853545 | Connectivity | Velocity MNT Tech | 2025-12-17 | 2025-12-29 | Yes | Completed through splicing in SJC to make Link Live. | Yes
2025-12-15 | Lawley | Resolved | FT574069 | DR1734940 | Connectivity | Velocity MNT Tech | 2025-12-17 | 2025-12-19 | Yes | Low Power levels caused due to faulty Cable | Yes
2025-12-15 | Lawley | Resolved | FT572887 | DR1749877 | Connectivity | Velocity MNT Tech | 2025-12-17 | 2025-12-18 | Yes | Low Power Levels. Cable was damaged by Rats. Replaced Drop Cable | Yes
2025-12-15 | Lawley | Resolved | FT567931 | DR1733156 | Connectivity | Velocity MNT Tech | 2025-12-17 | 2025-12-17 | Yes | Homedrop not connected properly at SJC. Plugged connector in. Service Restored | Yes
2025-12-15 | Mohadin | Open | FT571276 | No DR Supplied | Connectivity | Velocity MNT Tech | 2025-12-17 |  |  | Incomplete Installation. Drop Cable needs to go to the Pole. Tree cutting
2025-12-17 | Lawley | Resolved | FT553113 | DR1733351 | Connectivity | Velocity MNT Tech | 2025-12-17 | 2025-12-17 | Yes | Dirty Midcoupler | Yes
2025-12-17 | Lawley | Resolved | FT572992 | DR1733429 | Connectivity | Velocity MNT Tech | 2025-12-17 | 17/12/2025 | Yes | Dropcable was not connected properly at SJC. Plugged connector in | Yes
2025-12-17 | Mamelodi | Resolved | FT573759 | DR471279 | Connectivity | Velocity MNT Tech | 2025-12-08 | 2025-12-22 | Yes | Cleaned Dirty connection point in SJC. Light levels Improved. | Yes
2025-12-17 | Lawley | Resolved | FT574889 | DR1734800 | Connectivity | Velocity MNT Tech | 2025-12-17 | 2025-12-17 | Yes | Customer wanted assistance with TV Connection. | Yes
2025-12-17 | Mohadin | Resolved | FT575615 | DR1855513 | Connectivity | Velocity MNT Tech | 2025-12-17 | 2025-12-24 | Yes | Completed splicing in SJC to Restore Services | Yes
2025-12-17 | Lawley | Resolved | FT576826 | DR1734390 | Connectivity | Velocity MNT Tech | 2025-12-17 | 2025-12-20 | Yes | Broken Fibre Found. Respliced and Services Restored. | Yes
2025-12-17 | Lawley | Resolved | FT576854 | DR1734940 | Connectivity | Velocity MNT Tech | 2025-12-17 | 2025-12-19 | Yes | Low Power levels caused due to faulty Cable | Yes
2025-12-17 | Mohadin | In Progress | FT577495 | DR1854759 | Connectivity | Velocity MNT Tech | 2025-12-17 |  |  | SJC is Live. Drop Cable needs Replacement
2025-12-17 | Lawley | In Progress | FT579185 | DR1749857 | Connectivity | Velocity MNT Tech | 2025-12-18 |  |  | Light not reaching the dropcable. Cable needs replacement. No Access
2025-12-18 | Lawley | Resolved | FT580163 | DR1733319 | Connectivity | Velocity MNT Tech | 2025-12-18 | 2025-12-18 | Yes | Dropcable was Kinked due to not being Coiled in Slackblacket | Yes
2025-12-18 | Lawley | Resolved | FT580271 | DR1751323 | Connectivity | Velocity MNT Tech | 2025-12-19 | 2025-12-19 | Yes | Home Drop Replaced. Poor Coiling of Cable caused low power levels. Recoiling Recovering. Power Levels Improved. | Yes
2025-12-19 | Mamelodi | In Progress | FT584323 | DR470080 | Connectivity | Velocity MNT Tech | 2025-12-22 |  |  | No Access.
2025-12-19 | Lawley | Resolved | FT577737 | DR1734384 | Connectivity | Velocity MNT Tech | 2025-12-20 | 2025-12-24 | Yes | 7 Dropcables were destroyed due to Rats. Replaced HomeDrop | Yes
2025-12-20 | Lawley | Resolved | FT585434 | DR1748430 | Connectivity | Velocity MNT Tech | 2025-12-20 | 2025-12-22 | Yes | Feeder to Splitter was broken at Link Joint. Respliced | Yes
2025-12-22 | Lawley | Resolved | FT587570 | DR1733323 | Connectivity | Velocity MNT Tech | 2025-12-22 | 2025-12-22 | Yes | Dirty Midcoupler | Yes
2025-12-22 | Mohadin | Resolved | FT583069 | DR1855619 | Connectivity | Velocity MNT Tech | 2025-12-22 | 2025-12-29 | Yes | Completed through Splicing in the SJC. | Yes
2025-12-22 | Mohadin | In Progress | FT591759 | No DR Supplied | ONT Move | Velocity MNT Tech | 2025-12-23
2025-12-22 | Lawley | Resolved | FT593112 | DR1748657 | Connectivity | Velocity MNT Tech | 2025-12-23 | 2025-12-29 | Yes | No Issues Found. Power Meter Readings are Normal. | Yes
2025-12-22 | Lawley | Resolved | FT592246 | DR1734290 | Connectivity | Velocity MNT Tech | 2025-12-23 | 2025-12-24 | Yes | Drop Cable Damged due to Rodents. Drop Cable Replaced. | Yes
2025-12-22 | Lawley | Resolved | FT573912 | DR1733191 | Connectivity | Velocity MNT Tech | 2025-12-12 | 2025-12-29 | Yes | Dropcable was damaged and replaced. | Yes
2025-12-22 | Mohadin | Resolved | FT565908 | DR1855506 | Connectivity | Velocity MNT Tech | 2025-12-23 | 2025-12-24 | Yes | ONT Activated by MNT Technician. | Yes
2025-12-23 | Mohadin | Resolved | FT591532 | DR1855837 | Connectivity | Velocity MNT Tech | 2025-12-23 | 2025-12-24 | Yes | ONT Activated by MNT Technician. | Yes
2025-12-23 | Mamelodi | In Progress | FT585478 | DR470080 | Connectivity | Velocity MNT Tech | 2025-12-22 |  |  | No Access.
2025-12-24 | Lawley | Resolved | FT592707 | DR1734426 | Connectivity | Velocity MNT Tech | 2025-12-24 | 27/12/2025 | Yes | No Access. Feeder to Splitter was Broken. Respliced & Restored. | Yes
2025-12-24 | Lawley | Resolved | FT597081 | DR1734424 | Connectivity | Velocity MNT Tech | 2025-12-24 | 27/12/2025 | Yes | Broken feeder to Splitter. Respliced & Restored. | Yes
2025-12-26 | Lawley | Resolved | FT594344 | DR1734424 | Connectivity | Velocity MNT Tech | 2025-12-26 | 2025-12-27 | Yes | Broken feeder to Splitter. Respliced & Restored. | Yes
2025-12-29 | Mohadin | Pending Company | FT603665 | DR18563078 | Connectivity | Velocity MNT Tech
2025-12-29 | Mohadin | Pending Company | FT598336 | DR1855637 | Connectivity | Velocity MNT Tech |  |  |  | Minus 40 Current ONT RX Range as per master OES.
2025-12-29 | Lawley | In Progress | FT597870 | DR1730671 | Connectivity | Velocity MNT Tech | 2025-12-29 |  |  | Current ONT RX in range as per Master OES. No Access
2025-12-29 | Lawley | In Progress | FT604773 | DR1748392 | Connectivity | Velocity MNT Tech | 2025-12-29 |  |  | Minus 40 Current ONT RX Rang eas per master OES. Device not activated
2025-12-29 | Mohadin | Pending Company | FT596222 | No DR Supplied | Connectivity | Velocity MNT Tech
2025-12-29 | Mohadin | Pending Company | FT595180 | DR1855516 | Connectivity | Velocity MNT Tech |  |  |  | Current ONT RX in range as per Master OES.
2025-12-29 | Mohadin | Pending Company | FT599538 | No DR Supplied | Connectivity | Velocity MNT Tech
2025-12-29 | Mohadin | Resolved | FT606051 | DR1855619 | Connectivity | Velocity MNT Tech | 2025-12-22 | 2025-12-29 | Yes | Completed through Splicing in the SJC. | Yes

## ONT Swops
Date | Area | DR Number | Original SN# | New SN# | Responsible Technician | Returned (Y/N) | Reason for swop
2025-12-02 | Lawley | DR1734546 | ALCLB56593C0 | ALCLB477F74E | HJ - Velocity Fibre | Yes | Faulty Device
2025-12-05 | Lawley | DR1751562 | ALCLB465A9ED | ALCLB477B72F | HJ - Velocity Fibre | Yes | Faulty Device
2025-12-08 | Mohadin | DR1856977 | ALCLB480FBB8 | ALCLB480FA41 | Izeck - Velocity Fibre | No | Link light were still flashing after Reactivation.
2025-12-19 | Lawley | DR1752278 | ALCLB47CF992 | ALCLB47D5532 | HJ - Velocity Fibre | Yes | Faulty Device

## LAW Marketing
DR Number | Address | Comments | Contact Number | Rectifications
| 7170 Paul Street | Router not Working | 0815151531.
| 7136 Joy Street | Router not Working | 0783086470.
| 7200 Lesedi Street | Router not Working | N/A
| 7265 Tsakane Street | String is the problem, Torn apart | N/A
| 7175 Joy Street | Router not Working | N/A
DR1752416 | 704 / 705 Ipherial Crescent | Wires hanging | 0735887712.
DR1748445 | 7483 Tsakane Street | Not Lighting at all | 0672076523.

## Revenue Rescue
DR1750740
DR1748392
DR1750825
DR1749850
DR1748400
DR1748403
DR1750965
DR1748398
DR1748432
DR1748397
DR1750981
DR1748376
DR1748429
DR1748435
DR1748371
DR1748430
DR1748382
DR1748385
DR1748425
DR1748436
DR1750900 | DR175086
DR1748346
DR1748355
DR1748343
DR1748345
DR1748363
DR1749853
DR1749872
DR1748647
DR1749877